## Legend
ParkIQ — Franklin County, OH (pilot market) — Project admin workbook
Market slug: franklin_oh ¦ Boundary: Franklin County, GEOID 39049 ¦ Analysis CRS: EPSG:3735 NAD83 / Ohio South (ftUS)
HOW TO USE
Parameters: blue text = value you may edit. Yellow fill = BLANK you must decide before the phase that needs it.
Status column: SCOPE = value copied from SCOPE.md (still a placeholder); VERIFY = must be confirmed with a source; SET = you confirmed it (add citation); DECIDE = blank.
Source_Register: one row per dataset you download. Fill vintage, download_date, native_crs when you download.
Decision_Log: record every method choice before you apply it. Status: Proposed -> Accepted / Changed.
QA_Log: one row per check in SCOPE §10 / methodology §16.
OPEN ITEMS (live counts)
Parameters still DECIDE (blank) | 17
Parameters still VERIFY or SCOPE | 42
Sources not yet downloaded | 18
Decisions still Proposed | 14

## Parameters
group | parameter | value | unit | phase | status | source / citation | notes
Market | boundary | Franklin County, OH (GEOID 39049) |  | A | SET | User instruction (pilot market) | Market boundary; study area = +1 mile buffer
Market | analysis_crs | EPSG:3735 | NAD83 / Ohio South (ftUS) | A | SET | Matches Franklin County Auditor parcel service (WKID 102723 = 3735) | Units = US survey feet
Market | h3_resolution | 9 |  | A | SCOPE | SCOPE §2.2 [DECISION] | ~0.105 km2 avg hex area
Market | focus_submarkets |  | list | A2 | DECIDE |  | Chosen after the Session 2 county-wide demand scan
Site | min_parcel_sqft | 15000 | sqft | E | SCOPE | SCOPE §2.1 | At defaults yields ~39 stalls (<50). See Decision D-10
Site | max_parcel_sqft | 200000 | sqft | E | SCOPE | SCOPE §2.1 | At defaults yields ~518 stalls (>300)
Site | target_stalls_min | 50 | stalls | E | SCOPE | SCOPE §1.1
Site | target_stalls_max | 300 | stalls | E | SCOPE | SCOPE §1.1
Site | stall_area_sqft_gross | 320 | sqft/stall | C,E,H | SCOPE | SCOPE §2.1 [PARAMETER] (300–350 typical per scope)
Site | layout_efficiency | 0.9 | fraction | C,E,H | SCOPE | SCOPE §2.1
Site | setback_landscape_pct | 0.08 | fraction | E,H | SCOPE | SCOPE §2.1 | Check Columbus parking-lot landscaping/screening rules (CC 3312)
Site | max_slope_pct | 5 | percent | E | SCOPE | SCOPE §2.1
Site | min_frontage_ft | 60 | ft | E | SCOPE | SCOPE §2.1
Site | min_shape_index | 0.6 | ratio | E | SCOPE | SCOPE §2.1 | Metric = rectangularity (Decision D-09)
Site | improvement_ratio_max | 0.25 | ratio | E | SCOPE | SCOPE §5.5
Site | frontage_buffer_ft |  | ft | E | DECIDE
Demand | walk_shed_minutes | 3, 5, 8 | min | B,F | SCOPE | SCOPE §2.1
Demand | decay_weight_3min | 1 |  | B,C | SCOPE | SCOPE §5.2
Demand | decay_weight_5min | 0.6 |  | B,C | SCOPE | SCOPE §5.2
Demand | decay_weight_8min | 0.25 |  | B,C | SCOPE | SCOPE §5.2
Demand | walking_speed_m_s | 1.3 | m/s | A | VERIFY | SCOPE §5.1 [PARAMETER]; needs citation | Equals 255.9 ft/min
Demand | transit_radius_m | 400 | m | B | VERIFY | SCOPE §2.1
Demand | transit_demand_factor | 0.85 |  | B | VERIFY | SCOPE §2.1
Demand | high_freq_headway_max_min |  | min | B | DECIDE
Demand | rate_source_baseline_drive_share |  | fraction | B | DECIDE |  | Needed for mode adjustment (Decision D-06)
Demand | residential_offstreet_share |  | fraction | B | DECIDE |  | Or exclude residential demand (Decision D-07)
Demand | rate_office_per_employee | 0.80 / 0.05 / 0.05 / 0.02 / 0.00 | wd_day/wd_eve/we_day/we_eve/event | B | VERIFY | SCOPE App. C: 'ITE PG 6th ed. LU 701' [VERIFY]
Demand | rate_medical_per_bed | 2.50 / 0.80 / 0.90 / 0.50 / 0.00 | same | B | VERIFY | SCOPE App. C [VERIFY]
Demand | rate_university_per_student | 0.25 / 0.10 / 0.05 / 0.05 / 0.00 | same | B | VERIFY | SCOPE App. C [VERIFY]
Demand | rate_hotel_per_room | 0.40 / 1.00 / 0.50 / 1.10 / 0.00 | same | B | VERIFY | SCOPE App. C [VERIFY]
Demand | rate_restaurant_bar_per_ksf | 6.0 / 14.0 / 8.0 / 16.0 / 0.00 | same | B | VERIFY | SCOPE App. C [VERIFY]
Demand | rate_retail_per_ksf | 2.5 / 2.0 / 3.5 / 2.5 / 0.00 | same | B | VERIFY | SCOPE App. C [VERIFY]
Demand | rate_venue_per_seat_event | 0.33 | stalls/seat | B | VERIFY | SCOPE App. C: 0.85 drive share / 2.6 persons per car [VERIFY]
Demand | rate_residential_per_unit | 0.30 / 0.90 / 0.80 / 0.95 / 0.00 | same | B | VERIFY | SCOPE App. C [VERIFY]
Supply | private_effective_share | 0.5 | fraction | C | SCOPE | SCOPE §2.1
Supply | onstreet_stall_length_ft | 22 | ft | C | SCOPE | SCOPE §2.1 | Columbus meter layer may make this unnecessary downtown
Supply | dedupe_distance_m | 40 | m | C | SCOPE | SCOPE §5.3
Finance | assessed_to_market_ratio | 1.2 | ratio | H | VERIFY | SCOPE §2.1; calibrate from Franklin land listings
Finance | construction_cost_per_stall_usd | 6500 | USD | H | VERIFY | SCOPE §2.1 [VERIFY regional] | Get a Columbus-area paving contractor quote
Finance | soft_cost_pct | 0.15 | fraction | H | SCOPE | SCOPE §2.1 | Base = hard cost (Decision D-13)
Finance | opex_per_stall_year_usd | 450 | USD | H | VERIFY | SCOPE §2.1
Finance | tech_fee_pct_revenue |  | fraction | H | DECIDE
Finance | mgmt_fee_pct_revenue |  | fraction | H | DECIDE
Finance | property_tax_rate | 0.012 | fraction | H | VERIFY | SCOPE §2.1 | Replace with Franklin County effective commercial rate by taxing district (Auditor)
Finance | new_entrant_rate_discount | 0.1 | fraction | H | SCOPE | SCOPE §2.1
Finance | occupancy_caps | 0.85 / 0.60 / 0.40 / 0.70 / 0.90 | wd_day/wd_eve/we_day/we_eve/event | H | SCOPE | SCOPE §2.1
Finance | occupancy_curve_breakpoints |  | (x,y) pairs | H | DECIDE |  | Calibrate in Phase K
Finance | capture_share |  | fraction | H | DECIDE
Finance | billing_basis_and_units_by_daypart |  |  | H | DECIDE
Finance | operating_days_by_daypart |  | days/yr | H | DECIDE
Finance | event_weekday_share |  | fraction | H | DECIDE
Finance | permit_share / office_heavy_threshold |  | fraction | H | DECIDE
Finance | revenue_growth / opex_growth |  | %/yr | H | DECIDE
Finance | exit_cap_rate / selling_cost_pct |  | fraction | H | DECIDE
Finance | ground_lease_rent_pct / escalator / term |  |  | H | DECIDE
Finance | target_cap_rate | 0.075 | fraction | H | VERIFY | SCOPE §2.1
Finance | hold_years | 10 | years | H | SCOPE | SCOPE §2.1
Finance | discount_rate | 0.12 | fraction | H | SCOPE | SCOPE §2.1
Ranking | financial_weight | 0.7 |  | I | SCOPE | SCOPE §5.8
Ranking | suitability_weight | 0.3 |  | I | SCOPE | SCOPE §5.8
Ranking | shortlist_size |  | sites | I | DECIDE |  | SCOPE says 5–10

## Source_Register
source_id | provider | dataset | url / endpoint | vintage | download_date | license | native_crs | transformation | notes | planned session | status
S00 | US Census Bureau | TIGER/Line Counties (latest year) | https://www.census.gov/geographies/mapping-files/time-series/geo/tiger-line-file.html |  |  | Public domain | EPSG:4269 | NAD83 -> 3735 (same datum, no transformation) | Filter GEOID = 39049 | Session 1 | To download
S01 | Franklin County Auditor | Parcel polygons (open data portal) | https://auditor-fca.opendata.arcgis.com/ |  |  | Public domain per portal | EPSG:3735 | none | Replaces Regrid for this market (free). Values/land use may be in separate CAMA tables (Data Library / FTP) | Session 1 | To download
S01b | Franklin County Auditor | Appraisal/CAMA attributes (land value, building value, land use code) | https://franklincountyauditor.com/ftp |  |  | Public domain per portal [VERIFY] | table |  | Confirm which file carries land/improvement values + land use code; join on parcel ID | Session 1 | To download
S23 | City of Columbus | Base Zoning Districts | https://opendata.columbus.gov/datasets/96f7642a62f84db997f9e1db4a776995 |  |  | Open data, 'AS IS' terms | [fill] |  | Columbus has legacy Title 33 + Zone In Title 34 districts; downtown design-guideline zones A/B matter (see Decision D-15). Suburbs (Dublin, Upper Arlington, etc.) have their own zoning | Session 3 | To download
S20 | City of Columbus | Parking Meters (hourly rate, hours, max time) | https://opendata.columbus.gov/datasets/parking-meters/about |  |  | Open data, 'AS IS' terms | [fill] |  | On-street supply + rate signal. Check dataset currency (portal item dates back to 2017) | Session 4 | To download
S13 | Ohio DOT | Traffic count stations / AADT segments (TIMS / TMMS) | https://tims.dot.state.oh.us/ags/rest/services/Roadway_Information/Traffic_Count_Stations/MapServer |  |  | Public information per ODOT metadata | [fill] |  | C08 access/visibility | Session 5 | To download
S09 | COTA | GTFS schedule feed | https://mobilitydatabase.org/feeds/gtfs/tfs-216 (old entry points to replacement feed) or cota.com |  |  | [VERIFY] | WGS84 |  | Use the current producer URL shown in Mobility Database | Session 3 | To download
S04 | US Census Bureau LEHD | LODES WAC, Ohio, JT00, latest year | https://lehd.ces.census.gov/data/ |  |  | Public domain | blocks (join to TIGER blocks) |  | Also download OH TIGER blocks for geometry | Session 2 | To download
S05 | US Census Bureau | ACS 5-yr block groups: B08301, B25044, B25024 [VERIFY table IDs] | https://data.census.gov/ |  |  | Public domain |  |  |  | Session 3 | To download
S02/S03/S06 | Overture Maps Foundation | Buildings, Places (latest release) | https://overturemaps.org/ |  |  | ODbL / CDLA per theme [VERIFY] | EPSG:4326 |  |  | Session 2 | To download
S03/S06/S08 | OpenStreetMap | Ohio extract (streets, POIs, amenity=parking) | https://download.geofabrik.de/north-america/us/ohio.html |  |  | ODbL | EPSG:4326 |  |  | Session 2 | To download
S12a | HIFLD / CMS | Hospitals with beds | [VERIFY current source] |  |  | [VERIFY] |  |  | OSU Wexner, Grant, Riverside, Mount Carmel, Nationwide Children's etc. | Session 2 | To download
S12b | NCES | IPEDS institutions + enrollment | https://nces.ed.gov/ipeds/ |  |  | Public domain | lat/lon |  | Ohio State main campus dominates; also Columbus State, CCAD, Capital, Franklin Univ. | Session 2 | To download
S10 | Venues / Ticketmaster | Venue seats + events per year | venue websites; Ticketmaster Discovery API [VERIFY terms] |  |  | [VERIFY] |  |  | Nationwide Arena, Lower.com Field, Ohio Stadium, Schottenstein Center, Convention Center, KEMBA Live!, Ohio Theatre, Huntington Park | Session 2 | To download
S14 | FEMA | NFHL flood hazard areas, Franklin County | https://msc.fema.gov/portal/ |  |  | Public domain |  |  | Scioto & Olentangy floodways run through the core | Session 5 | To download
S15 | US EPA | FRS + ACRES / Cleanups in My Community | https://www.epa.gov/frs |  |  | Public domain |  |  |  | Session 5 | To download
S18 | USGS | 3DEP 1/3 arc-second DEM | https://apps.nationalmap.gov/downloader/ |  |  | Public domain | EPSG:4269 |  |  | Session 5 | To download
S22 | City of Columbus | Building permits / planned development | https://opendata.columbus.gov/ |  |  | Open data |  |  | Pipeline risk (C10) | Session 5 | To download
S24 | City of Columbus | Downtown parking study (2023–24) and Parking Impact Studies | https://www.columbus.gov/ (Mobility & Parking Services) |  |  | [VERIFY] | PDF |  | Use for demand QA (±25%) and supply calibration | Session 4 | To find
S07 | Field survey (analyst) | Posted rates at off-street lots/garages | own observations |  |  | Own data | lat/lon |  | Replaces app listings unless licensed. Template in methodology App. E | Session 4 | To collect

## Decision_Log
id | date | phase | question | options considered | choice | rationale | impact | status
D-01 | 2026-09-24 | A | Pilot market | — | Franklin County, OH | User decision | All phases | Accepted
D-02 | 2026-09-24 | A | Analysis CRS | EPSG:3735 vs 3753/6549 (HARN/2011) vs UTM 17N | EPSG:3735 NAD83 Ohio South ftUS | Matches Auditor parcel service; no reprojection of the largest layer | All | Proposed
D-03 | 2026-09-24 | A | Study extent strategy | Full county at full detail; fixed downtown; two-stage | Two-stage: county-wide demand scan (Session 2), then full network method in 1–3 focus submarkets chosen from the scan | Manual network work scales poorly to 1,400 km2; choice stays data-driven | B–J | Proposed
D-04 | 2026-09-24 | A | Grid | H3 r9 vs equal-area hexes | H3 r9 via Generate Tessellation (Pro 3.1+) | SCOPE §2.2 | All | Proposed
D-05 | 2026-09-24 | A | Network backend | Network Analyst vs QGIS/QNEAT3 | [your choice] | Depends on your Network Analyst license | B,C,F | Proposed
D-06 | 2026-09-24 | B | Mode-share adjustment | raw ACS drive share; relative to rate baseline; none | Relative: local / baseline drive share | Avoids double-discounting observed-vehicle rates | B | Proposed
D-07 | 2026-09-24 | B | Residential demand | offstreet_share parameter vs exclude | [decide] | ACS has no direct measure | B | Proposed
D-08 | 2026-09-24 | B | Allocation normalization | conserving vs accessibility-style | Demand/supply conserving (weights / sum of weights per origin) | Gap must be in stall units | B,C | Proposed
D-09 | 2026-09-24 | E | Shape index metric | rectangularity vs Polsby-Popper | Rectangularity = area / min-area bounding rectangle | Tracks stall-layout efficiency | E | Proposed
D-10 | 2026-09-24 | E | Size vs stall range | sqft only; stalls only; both | Apply both; stall range binds | Scope defaults are inconsistent | E | Proposed
D-11 | 2026-09-24 | G | Dirichlet form | flat vs centered | Flat (alpha = 1) | Neutral | G | Proposed
D-12 | 2026-09-24 | H | Occupancy function | f(gap_ratio) only vs + absorption cap | min(cap, g(gap_ratio), capture x unmet / stalls) | Prevents big lots filling from small gaps | H | Proposed
D-13 | 2026-09-24 | H | Soft cost base | hard cost vs hard + land | Hard cost |  | H | Proposed
D-14 | 2026-09-24 | I | Financial ranking metric | yield-on-cost vs IRR vs NPV | Yield-on-cost (buy) | Less exposed to exit assumptions | I | Proposed
D-15 | 2026-09-24 | E | Zoning screen for Columbus | legacy districts only vs + Zone In + downtown design zones | Build zoning_screen table covering Title 33, Title 34 (Zone In) and Downtown zones A/B; suburbs separately | Downtown guidelines prohibit non-accessory lots in zone A; CoA review everywhere downtown [VERIFY current code] | E | Proposed

## QA_Log
check_id | run_id | stage | check | threshold | result | count | passed (Y/N) | date / notes
QA-01 |  | Ingest | All layers in EPSG:3735 | 100%
QA-02 |  | Ingest | Null/invalid geometry after repair | 0
QA-03 |  | Ingest | Duplicate parcel_id / facility_id | 0
QA-04 |  | Grid | Hex overlaps/gaps | 0
QA-05 |  | Demand | Sum hex demand = sum anchor demand (each daypart) | exact
QA-06 |  | Demand | Downtown weekday vs published study | ±25%
QA-07 |  | Supply | Stated vs estimated capacity (median abs % error) | ≤20%
QA-08 |  | Rates | IDW cross-validation error | ≤20%
QA-09 |  | Screen | Every evaluated parcel has screen_reason | 100%
QA-10 |  | Scoring | Weights sum to 1; composite 0–100; unique ranks | exact
QA-11 |  | Finance | Hand check of 3 sites vs workbook | $1
QA-12 |  | Maps | Title/legend/scale/sources/run ID on every map | 100%
QA-13 |  | Package | Every memo number traced | 100%